## Sheet1
Planning, Strategy and Study Schedules (Revised)
| 2010 | [9 empty] | 2011 | [11 empty] | 2012
Comprehensive Plan | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Community Assessment | bar: 2010 Mar to 2010 Sept
Community Participation | bar: 2010 Mar to 2011 Feb
Community Agenda | bar: 2010 Aug to 2011 May
Review by ARC/DCA | bar: 2011 Jun to 2011 Sep
Strategic Eco Dev Plan | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Research & Analysis | bar: Feb to Jun
Action Strategy | bar: Jul to Oct
Marketing Strategy | bar: Jul to Oct
Final Report/Presentation | bar: Oct
HBR Corridor Study | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Vision & Data Collection | bar: Apr to May
Short/Mid-Range Alternatives | bar: Apr to Jul
Land Use and Economic Analysis | bar: Apr to Oct
Long-Range Alternatives | bar: Aug to Dec
Final Master Plan | bar: Dec to Mar