## PROJECT UPDATE
Project Phase Matrix
| Project | Description | PM | Remarks/Status
Planning and Feasibility Studies
1 | Big Creek Bridge Road | Project Development/ Build Support & Consensus for Big Creek Bridge Road over GA 400 between the interchanges of HBR and Mansell Road. | Chovan | The Gresham Smith team will be providing the study documentation within the next 30 days at which time the contract will be concluded.
Advertising for Consultants
2 | Holcomb Bridge Road Corridor Study | Comprehensive Planning Study in the area surrounding the Holcomb Bridge Road and GA 400 interchange. The Study includes developing traffic improvements and aesthetic enhancements that will support potential redevelopment in the area. | Antweiler | The RFP for the project was advertised in the newspaper November 10th with proposals due December 14th. Staff anticipates bringing recommended consultant for selection to January TCM.
3 | Chattahoochee River Pedestrian Improvements | This project will construct a multi use trail along SR 9 over the Chattahoochee River Bridge to address deficient bicycle/pedestrian access. The bridge connects Roswell and Sandy Springs. | Dell-Ross | Signed PFA sent to GDOT for approval Oct 13. Staff will move forward with consultant procurement as soon as the GDOT funds are recognized and the requisition is approved. Staff is using a 2-tier selection process and will bring a consultant recommendation to February TCM. SOQ's were received December 10th. NTP is anticipated in March/April 2011.
4 | Hardscrabble Green Loop Phase 1 | This project will construct a multi use trail along Hardscrabble Road from Roswell High School to Sweet Apple Elementary School, sidewalk improvements along Hardscrabble Road and several intersection improvements along Hardscrabble Road. | Dell-Ross | 16 firms submitted SOQ's, which were received on 10/14/2010. Staff has short listed three firms: LPA, QK4, and RS&H. Staff has begun negotiation with RS&H and hopes to bring a recommendation for approval to TCM in December.
5 | Sun Valley Connector | This project will extend Sun Valley Drive to Warsaw Road and Old Ellis Road to Mansell Place. The project will improve connectivity for traffic going north on SR 9 from Mansell Road and Old Roswell Road. | Buckley | Staff has broken this project into 3 phases for inclusion in the Master Plan. Staff has selected Edwards-Pitman Environmental to perform the environmental screening and wetlands delineation for this project ($6881.91). Wetlands delineation is complete. Environmental screening was submitted on Nov 8. Mayor & Council has given permission to staff to ask NFCID to help with funding various phases of the project. Survey received on Dec 10. Staff is beginning to fine-tune concepts in preparation for January NFCID meeting.
6 | Oxbo Road Intersection Improvements | Intersection Improvement project at Oxbo Road and SR 9. The project provides better north-south connectivity through Elm Street and better east-west connectivity along the relocated Oxbo Road. Related to the Maple Street/Vickery Creek redevelopment efforts by Granholm. | Buckley | Staff will be advertising this project as a turnkey design project using the 2-tier QBS selection process. Staff has shortlisted 4 teams (LPA, CPL, KHA, H&L). Purchasing has sent out the RFP. Proposals are due Jan 5. NTP is anticipated in March 2011.
Concept Development Phase
7 | Historic Gateway Improvements | This project will remove the Reversible Lane System along South Atlanta Street with two through lanes in each direction from SR 120/Marietta Highway to the intersection of Riverside Road/Azalea Drive at the Chattahoochee River. It also includes an intersection improvement at Riverside/Azalea and a new bridge over Vickery Creek. | Dell-Ross | Signed PFA sent to GDOT Oct 13. The contract has been signed by both parties and has been executed. NTP was given Nov 1. GDOT has authorized PE funds. Schedule for PFA submitted to Mac Cranford on Nov 12. PB's phone survey of residents has begun and should be finished by Christmas.
8 | SR9 ATMS | This project will provide adaptive signal timing and remote monitoring of congestion and incidents along the SR 9 corridor from Abernathy Road in the City of Sandy Springs to the Forsyth County line in the City of Milton. Some of the Traffic Control Center (TCC) components will be provided through this project. | Rauf | Concept Report approved by GDOT. Design Phase initiated July 2009. PFPR held on 12/08/09. FFPR held 3/23/10. Delayed letting. TIP updated to 2011 letting.
9 | Holcomb Bridge Middle School Sidewalks Phase 2 | This project will provide 7,000 LF of 8' to 10' wide multi-use along the south side of HBR/SR 140, beginning from Steeple Chase Dr West to South Holcomb Bridge Way/Nesbit Ferry Road. Due to funding constraints, this project will be constructed in segments. Segment I, about 1,970 LF, will start from Steeple Chase Dr to the Horizon @ Roswell office condo (opposite side of East Village/ Super Target) | Osse | Consultant is updating plans to reflect comments from 2nd submittal.
Preliminary Design Phase
10 | MARTA Offset Project: Semmi-Seat Improvements | This project consists of installing Simme-seats at 13-15 locations. (Note: Shelters are a separate project) | Buckley | Plans submitted to GDOT & MARTA on 12/03/10 for review.
11 | MARTA Offset Project: Multiple Pedestrian Improvements | This project will construct a couple small sections of new sidewalks or crosswalks within a 0.75 mile radius of MARTA bus routes. | Buckley | Plans submitted to GDOT & MARTA on 12/03/10 for review.
12 | MARTA Offset Project: GA 400 Bridge Pedestrian Improvements | This projects will construct new sidewalks, crosswalks, and pedestrian signals along Holcomb Bridge Road over the GA 400 bridge. | Antweiler | MARTA signed IGAs on July 26th. NTP given to design consultant August 10th. Staff and consultant had kickoff meeting with GDOT Sept 1st. Surveying is complete. Consultant developing prel. plans and expect submittal to GDOT 12/10.
13 | MARTA Offset Project: Bus Shelter Improvements | This project consists of installing bus shelters at 8-10 locations. (Note: Semmi-seats are a separate project) | Antweiler | MARTA signed IGAs on July 26th. NTP given to design consultant August 10th. Survey work underway. Received letter from MARTA approving locations. Consultant preparing preliminary plans and expect submittal to GDOT by 12/10.
14 | MARTA Offset Project: Sidewalk Projects | This series of projects will construct new sidewalks, crosswalks, and pedestrian countdown signals within a 0.75 mile radius of MARTA bus routes. | Antweiler | MARTA signed IGAs on July 26th. NTP given to design consultants August 10th. Consultants proceeding with Preliminary Plans. Staff reviewing Batch #2 prel. plans. Expect Batch #1 prel plans submittal to city by 12/10.
15 | SR140 ATMS | This project will provide adaptive signal timing and remote monitoring of congestion and incidents along the SR 140/Holcomb Bridge Road corridor from SR 9/120 to Barnwell Road. Some other components could be upgrades to the Traffic Control Center (TCC), travel time, count stations. Let date June 2012. | Rauf | Projects combined to save money on concept and design. Approved by City Council at March 2010 meeting to award concept and design to URS for $174,113. NTP executed 6/14/10 in the amount of $167,962 with reduced scope of work. Scope reduced due to reduction in federal funds. Kick off meeting 6/23/10. Concept report submitted to GDOT 9/03/2010. Resubmitted concept report after addressing GDOT's comments on 11/17/10.
16 | SR 92 ATMS | This project will provide adaptive signal timing and remote monitoring of congestion and incidents along the SR 92/Crossville Road corridor from SR 9/120 to the Cobb County line. Some other components could be upgrades to the Traffic Control Center (TCC), travel time, count stations. Let date June 2012.
17 | North Fulton Comprehensive Transportation Plan (NFCTP) | Five (5) North Fulton Cities (Alpharetta, Johns Creek, Milton, Roswell, and Sandy Springs) are coordinating with the Atlanta Regional Commission (ARC) to initiate the North Fulton Comprehensive Transportation Plan (NFCTP). ARC and the cities believe a regional transportation plan is vital to the area to identify regional needs and to coordinate transportation funding priorities. | Chovan | The Kimley-Horn team is preparing the final documentation within the next 30-45 days. It is expected that M&CC will be asked to approve the Study in October.
Acquisition Phase
18 | Oak Street Streetscape - Section I | Section I of the Oak Street Streetscape project starts at SR9 and ends at Bush Street. The enhancement will include brick paver sidewalks with a four foot landscape strip on the north side and a ten foot multiuse pedestrian walkway with four foot landscape strip on the south side. To further enhance the corridor, all overhead utilities will be replaced with underground utilities. | DeMarco | AT&T final designs will be done in a week. GP to start is 60 days. AT@T will need EDT OR CITY to Locate grass strip at Stations 15+00 and 14+00 exactly (i e via survey ) for final box loction with 10 day notice to city . AT&T's Plans are due by the end of the month. Met with AT&T on site and coordinated with Charter will need some GDOT permits as well. GP has GDOT permits. GP's Decorative Lighting instatlation agreement will be on the Trans. Committee Agenda. SOCA has been rewired by Meer Electric and GP will complete pole instalation this week. AT&T will select Contractor on December 15. AT&T will set up meeting with contractor and City staff on-site to establish box locations. GP Poles are all in. Wires already being transferred to new poles. Meer Electric has reconfigured four businesses so far and is waiting for GP so they can run wire. K-9 business is going slow on easement for replacement pole.K-9's easement was refined and resubmitted by GP. Met with GP Re: Street lights. By moving the phase 2 vehicle light to the NW Corner of cemetery adding two pedestrian lights (one in the middle of the cemetery and one at across at Krispy Kreem) we get Street lights all along Phase One. Meer wired two more businesses... two more to go. We will need a change order to the contract with Meer for wiring the 8 business for AT&T and Cable.
Final Design Phase
Procurement Phase
19 | Crabapple Road Sidewalks | Sidewalk additions along Crabapple Road to improve connectivity in the surrounding area. | Osse | Estimated Const. cost $191,571.62. Bids due Thursday, Sept. 30, 2010 at 12:00 pm. Contract in the amount of $179,563.87 awarded to JJE at Council on Nov 8. Finalizing and negotiating change order and cost with contractor JJE.
20 | Holcomb Bridge Middle School Sidewalks Phase 1 | Phase 1 is filling sidewalk gap on the north side of HBR/SR 140 within a 1/2 mile radius of Holcomb Bridge Middle school. | Osse | Last parcel, Holcomb Pond management has agreed in concept. (Waiting on corporate review/signature). Plans are modified to eliminate easement from Pond. Procurement schedule: 12/8: Ad ~ 12/23: Pre-bid meeting ~ 1/6: Bids due. Total estimated construction cost $104,056.66.
Construction Phase
21 | Midtown Roswell | This LCI Project will include stamped asphalt in two-way-left-turn-lane, new sidewalks, street trees, and pedestrian-scale lighting. | Phillis | Construction is underway. New medians notices sent.
22 | Grimes Bridge @ Norcross/Warsaw Roundabout | This project will create the City of Roswell's first roundabout. The roundabout will have five legs connecting Grimes Bridge Road, Norcross Street, Warsaw Road, and Melody Lane. | Phillis | Low bidder is CMES, Inc. at $579,198.60. A utility meeting was held on October 19 at the site. The Contractor started clearing October 25th.
23 | SR9 (Alpharetta Hwy) @ SR140 (HBR) Intersection Improvements | This project will add a second left turn lane on three approaches (NB SR 9/120, WB SR 140, and EB SR 92) and extend some sections of raised median along SR 9 and SR 140. | DeMarco | The GDOT letting for the project took place on June 18, 2010. The low bidder was Baldwin Paving with a bid of $1,244,322.74. Roswell's 20% match was approved by Council on Aug 9 and submitted to GDOT. Preconstruction meeting on Oct 8, Contractor to mobilize on Nov. 1. Groundbreaking scheduled for Nov 12.
24 | Warsaw Road Sidewalks | Sidewalk additions along Warsaw Road to improve connectivity in the surrounding area. | Phillis | Construction under way.
Non - CIP Projects
25 | Mansell Extension | This project will extend Mansell Road from its current terminus at SR 92 south to a new intersection with SR 9/120 at Mansell Circle. | Dell-Ross | Funds for survey were approved in FY11 budget. Once the survey is complete, staff will be designing this in-house. Survey NTP was given on Oct 20. Property owners have been notified about survey crews. Terramark will be tieing this survey database into the Mansell at 92 survey that we provided them. The database is expected to be delivered by Dec 17. Steve is meeting with Rich, Kay and Bryant Poole on Dec 10 to discuss GDOT funding potential.
26 | Grimes Bridge Traffic Calming | This project will eliminate the need for an unwarranted traffic signal at the Shadowbrook subdivision along with reducing speed along Grimes Bridge Road. | Rauf | Discussed at April TCM. Staff to continue looking at options.
27 | Riverwalk Emergency Access | This project will provide a 16' wide/450' long emergency access to the Riverwalk Condo Community | Osse, Buckley | Design is complete. Project is on hold until funding is available. Staff will request funding for construction as part of the budget process for FY 2012.
28 | Leita Thompson Deceleration Lane | This project will provide a right turn lane into Leita Thompson Memorial Park. | Nervais | Design is complete. Encroachment permit has not been returned to GDOT. Project is on hold until funding is available. Staff will coordinate with GDOT regarding whether the permit should be obtained now or to hold. Staff will request funding for construction as part of the budget process for FY 2012.
29 | SR 9 at SR 120 Intersection Improvement | This project will fix the turning movement from Southbound SR 9 to Westbound SR 120. Large trucks attempting this right turn are hitting the wall in the Square to avoid hitting a ped pole in the pedestrian island. | Dell-Ross | Staff's concept with mast arms and 2 raised islands was approved in July, assuming no impacts to the pecan tree. Staff has finished preliminary plans and sent blank signal plans to Muhammad for design. Utility plans will be sent out for markups.
30 | Willow Springs - Traffic Calming |  | Buckley | 2 Splitter islands will cost no more than $10,000, and will likely be built using in-house forces. Plans are 50% complete. TCM has allowed the petition process to begin. If the petition is approved, the design will be finalized.
31 | Mansell at 92 Intersection Improvement | This project will add a right turn lane on SB Mansell Road approaching SR 92 going WB. | Dell-Ross | ComDev and Transportation met with Aldi/Racetrac engineers on 12/10/10 to coordinate site development with intersection improvements. RDOT and site engineers will be developing several concepts for driveway access and dual right turn improvements over the next two weeks, and then will decide on a concept acceptable to all.
32 | Amana Academy site | This is vacant sites formerly "Amana Academy" school. RDOT is investigating the feasibility of a street connectivity with the parcel on the west, which is a truck unloading area for the xxxxxx shopping center. | Osse | Initial const. cost estimates $100,384.80. On Hold per Steve. Fire is considering other locations (i.e. Terramont Park. But Martin Landins and Terramont S/D opposes)
33 | Etris Road Sidewalk | Request to provide sidewalk on the east side of Etris Road, from Cagle Rd to Cox Rd
34 | Myrtle Street Extension
35 | Forrest Street Extension
36 | Oxbo Bridge Replacement
37 | Pleasant Hill Extension
38 | Old AL Road at Old AL Connector Intersection Improvement
39 | The Chandlery Sidewalk Expansion | This project will convert an existing 2-car space on-street parking in front of "The Chandlery" at "960 Canton Street" to brick sidewalk. Part of it to be used for sidewalk café. | Osse | Bids are in: Concrete Creations(They did Ceviche for $9,000) = $8,875. PE Structures = $18,800.00 Strickland Construction = No bid. Steve will discuss using safety money for construction w/ Kay.
40 | Cherry Street Improvements | This concept is to make improvements to Cherry Street. | Buckley | Staff has developed three concepts for improvements to Cherry Street. Construction costs for the three improvements range from $140,000 to $210,000. Clyde is estimating ROW costs. Concepts were presented at November TCM. Per council direction, staff will talk with business owners to guage level of interest and support for potential improvements.
41 | Plum Street Improvements | This concept is to widen from a one lane to 2-11 foot lanes and extend Plum Street to SR 9. | Dell-Ross | Staff has developed four concepts to present at December TCM.
42 | Crabapple Road Median Islands | This project will install 7 median Islands along Crabapple Road from Station Parkway to Strickland Road. | Nervais | Procuring bids
43 | Midtown Gap | This project will be to complete the streetscape on SR 9, beginning at Mansell Circle and continuing north on SR 9 588 feet. | DeMarco
44 | Midtown Median Islands |  | DeMarco | Clyde is in the process contacting property owners

## Capital Proj Funding
Project | Grant | 95B | 2000B | IF | Gen Fund | TOTAL
HBR S/W to GA 400 05TRA003
DESIGN |  |  | 72500 |  |  | 72500
ROW |  | 0 |  |  |  | 0
CST |  | 0 | 237500 |  | 450686 | 688186
Grand Total | [5 empty] | 760686
Mimosa Boulevard Extention 06TRA004
DESIGN | [5 empty] | 0
ROW |  |  |  |  | 450 | 450
CST |  |  |  |  | 551994 | 551994
Grand Total | [5 empty] | 552444
Steeplechase/ Fouts Trail 07TRA002
DESIGN |  |  | 0 |  | 556 | 556
ROW |  |  |  |  | 1900 | 1900
CST |  |  |  |  | 352440 | 352440
Grand Total | [5 empty] | 354896
Crabapple/ Chaffin Intersection 05TRA005
DESIGN | 15742 |  |  |  | 60233 | 75975
ROW |  |  |  |  | 28155 | 28155
CST | 267822 |  |  | 250000 | 285920 | 803742
Grand Total | [5 empty] | 907872
Crabapple/ Rucker Intersection 04TRA002
DESIGN |  |  |  | 37893 |  | 37893
ROW |  |  |  | 129700 |  | 129700
CST |  |  |  | 1061039 |  | 1061039
Grand Total | [5 empty] | 1228632
Hardscrabble/ Chaffin Intersection 05TRA011
DESIGN |  |  |  | 0 |  | 0
ROW | [5 empty] | 0
CST |  |  |  | 457090 |  | 457090
Grand Total | [5 empty] | 457090
HBR/ Alpharetta Hwy 05TRA013
DESIGN |  |  |  | 89593 |  | 89593
ROW | 279532 |  |  | 20250 |  | 299782
CST |  |  |  | 112347 |  | 112347
Grand Total | [5 empty] | 501722
Old Alabama Connector 05TRA012
DESIGN | [5 empty] | 0
ROW | [5 empty] | 0
CST |  |  |  | 453167 |  | 453167
Grand Total | [5 empty] | 453167
Midtown Roswell Redevelopment 05TRA007
DESIGN | 2931 |  |  |  |  | 2931
ROW |  |  |  |  | 563696 | 563696
CST | 2189159 |  |  | 85000 | 1025959 | 3300118
Grand Total | [5 empty] | 3866745
Midtown Roswell Hog Waller Crk 05TRA019
CST |  |  |  |  | 40000 | 40000
Grand Total | [5 empty] | 40000
Grimes Bridge Rd Bridge Replacement 05TRA002
DESIGN |  | 17878 |  | 47997 | 44591 | 110466
ROW | [5 empty] | 0
CST | [5 empty] | 0
Waterline Relocation | [5 empty] | 0
Grand Total | [5 empty] | 110466
Hembree Rd Bridge Replacement 05TRA024
DESIGN |  |  |  | 3736 |  | 3736
ROW |  | 3171 |  | 9316 |  | 12487
CST |  | 0 |  | 96954 |  | 96954
Grand Total | [5 empty] | 113177
Chatt/ King/ SR 9 Intersection TS99NI50
DESIGN |  |  |  | 21511 |  | 21511
ROW | [5 empty] | 0
CST | [5 empty] | 0
Grand Total | [5 empty] | 21511
Citywide Reconstruction/ Resurfacing 05TRA006
Supplies |  |  |  |  | 2178577 | 2178577
CST |  |  |  |  | 371256 | 371256
Grand Total | [5 empty] | 2549833
Sidewalk Connectivity 06TRA001
CST |  |  | 9529 |  | 520608 | 530137
Grimes/ Norcross/ Warsaw 08TRA001
DESIGN |  |  |  |  | 110943 | 110943
Contingency |  |  |  |  | 66000 | 66000
Contingency |  |  |  | 539000 |  | 539000
Grand Total | [5 empty] | 715943
SR140 ATMS 08TRA005
DESIGN |  |  |  |  | 150000 | 150000
SR9 ATMS 08TRA004
DESIGN |  |  |  |  | 14262.09 | 14262.09
CST |  |  |  |  | 396013 | 396013
Grand Total | [5 empty] | 410275.09
SR92 ATMS 09TRA005
DESIGN |  |  |  |  | 150000 | 150000
Upper Hembree Underpass 08TRA002
CST | [5 empty] | 0
Contingency |  |  |  |  | 70000 | 70000
Grand Total | [5 empty] | 70000
Hardscrabble/ King 09TRA007
Contingency |  |  |  |  | 130000 | 130000
NFCTP 09TRA008
DESIGN |  |  |  |  | 100000 | 100000
ATMS Master Plan 09TRA009
DESIGN |  |  |  |  | 99670 | 99670
Willeo Road Sidewalk 05TRA037
DESIGN | [5 empty] | 0
ROW |  |  | 911 |  |  | 911
CST |  |  |  |  | 183430 | 183430
Grand Total | [5 empty] | 184341
Pine Grove Drainage B987D08
DESIGN |  | 82830 |  |  |  | 82830
ROW
CST
Grand Total | [5 empty] | 82830
Northern Connector 09TRA016
DESIGN |  |  |  |  | 367704 | 367704
ROW |  |  |  |  | 19334
CST
Grand Total | [5 empty] | 367704
Historic Roswell Railroad Trail
DESIGN |  |  |  |  | 25645 | 25645
Grand Total | [5 empty] | 25645
Upper Hembree Road Resurfacing 05TRA006
CST |  | 290340 |  |  |  | 290340
Grand Total | [5 empty] | 290340
Bridge Maintenance Program 09TRA011
CST |  |  |  |  | 409080 | 409080
Road Safety Program 09TRA013
CST |  |  |  |  | 81603 | 81603
Traffic Calming 09TRA014
CST |  |  |  |  | 25000 | 25000
Street Light Program 09TRA015
CST |  |  |  |  | 26926 | 26926
Westside Parkway 05TRA034
DESIGN |  |  |  | 18489 | 25462 | 43951
Available to Reallocate
Old Alabama Sidewalk and Ped |  |  |  |  | 7783 | 7783
Holcomb Br/ GA 400 Study |  |  |  |  | 2000 | 2000
Skid Steer Loader |  |  |  |  | 1702 | 1702
Bike Shoulders-Crabapple/ Coleman |  |  |  |  | 40000 | 40000
Upper Hembree Underpass |  |  |  |  | 41046 | 41046
Truck Mounted Attenuator |  |  |  |  | 33000 | 33000
Grand Total | [5 empty] | 125531
Total Unspent Funds | 2736513 | 0 | 247940 | 3283371 | 8029000 | 14296824
Less Encumbrance | -18673 | -394219 | -72500 | -149711 | -1027624 | -1662727
Total | [5 empty] | 12634097

## shortsheet
Planning and Feasibility Studies |  | Final Design Phase
1 | Big Creek Bridge Road | 20 | Holcomb Bridge Middle School Sidewalks Phase 1
2 | Holcomb Bridge Road Corridor Study | Procurement Phase
Advertising for Consultants |  | 21 | Grimes Bridge at Norcross/Warsaw Roundabout
3 | Chattahoochee River Pedestrian Improvements | 22 | Warsaw Road Sidewalks
4 | Historic Gateway Improvements | 23 | SR 9 at SR 140 Intersection Improvements
5 | Green Loop with Hardscrabble Road Intersection Improvements | 24 | Crabapple Road Sidewalks
6 | Sun Valley Connector | Construction Phase
7 | Oxbo Road Intersection Improvements | 25 | Swaybranch Drive Extension
Concept Development Phase |  | 26 | Midtown Roswell
8 | SR9 ATMS | 27 | Crabapple at Rucker
9 | Holcomb Bridge Middle School Sidewalks Phase 2 | 28 | Lake Charles Dr Sanitary Sewer
Preliminary Design Phase |  | 29 | HBR Sidewalks
10 | MARTA: Semmi-Seat Improvements | Non - CIP Projects
11 | MARTA: Multiple Pedesrian Improvements | 30 | Mansell Extension
12 | MARTA: GA 400 Bridge Pedestrian Improvements | 31 | Grimes Bridge Traffic Calming
13 | MARTA: Bus Shelter Improvements | 32 | Riverwalk Emergency Access
14 | MARTA: Sidewalk Projects | 33 | Leita Thompson Deceleration Lane
15 | SR140 ATMS | 34 | SR 9 at SR 120 Intersection
16 | SR92 ATMS | 35 | Pleasant Hill St Extension
17 | ITS Master Plan | 36 | Mimosa Blvd relocation
18 | NFCTP | 37 | Willow Springs - Traffic Calming
Acquisition Phase |  | 38 | Mansell at SR 92 Intersection Improvements
19 | Oak Street Streetscape - Section 1