## INFORMATION ITEMS
INFORMATION ITEMS | DUE DATE | STATUS | COMMENTS
Oak Street Utilities |  | Staff is working to finalize the agreement with GA Power. The Utility Agreement should be ready in time for the February Committee agenda.
SR9 - Removal of Reversible Lane Update |  | Staff has continued to push forward with the concept of removing the reversible lanes along Atlanta Street while concurrently working on the Chattahoochee River pedestrian crossing project. Staff will be ready to present their strategy to complete the entire project in phases at the February Committee meeting so that Mayor and City Council will have a better idea of the project lengths and potential funding sources over the next 6-8 years. Staff is also planning to meet with the GDOT managerial staff to determine the best course of action to move the project forward. | At this time, staff feels it is still too early to roll the concept out in a Public Meeting format because of the many unknowns in the project schedule and required funding.
Grimes Bridge/ Norcross/ Warsaw Roundabout |  | Ralph N Brown and Associates has been contracted to complete the ROW Acquisition for this project. He is currently in negotiations with all of the property owners. We are hoping to return to the February Committee Meeting with signed Options. | A second Public Information Open House is scheduled for February 4th from 6:30 p.m. to 8:00 p.m. at the Adult Recreation Center.
Project Phase Matrix |  | Attached list showing current status of ongoing Transportation Projects. | See attached