Table 14.1

Short-Term Work Program, City of Roswell, FY 2010-2011 to FY 2014-2015

| Plan Element | Description | FY 10-11 | FY 11-12 | FY 12-13 | FY 13-14 | FY 14-15 | Total Cost (If Any) | Impact Fee Eligible (mark with X) | Responsible Department or Agency |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Population | Monitor regional and U.S. Census Bureau estimates of the City’s population | X | X | X | X | X |  |  | Community Development |
| Population | Monitor and publicize any adult literacy programs available to Roswell’s residents | X | X | X | X | X |  |  | Community Relations Office |
| Population; Development Impact Fees | Update population and functional population projections as needed to support annual updates of the Capital Improvement Element | X | X | X | X | X |  |  | Community Development |
| Housing | Maintain data on issuance of housing starts (building permits) for estimates of population and housing | X | X | X | X | X |  |  | Community Development, Building Division |
| Housing | Identify any concentrations of substandard housing units and use community development funds to help fund improvements | X | X | X | X | X |  |  | Community Development (CDBG if available) |
| Housing | Continue to enforce the standard housing code | X | X | X | X | X |  |  | Community Development |
| Housing | Maintain the City’s public housing program and determine appropriate future activities/programs | X | X | X | X | X |  |  | Housing Authority |
| Housing | Monitor available state and federal housing programs and disseminate information to individuals and groups in need of such program resources | X | X | X | X | X |  |  | Community Development |
| Housing | Work on affordable housing study | X | X | X | X | X |  |  | Community Development |
| Economic Development | Gather information on properties suitable for office development and provide market information to developers, the Greater North Fulton Chamber of Commerce, Georgia Power Company, Fulton County, etc. | X | X | X | X | X |  |  | Roswell EDD; GNFCC; Ga. Power Co. MACOC, Fulton County ED |
| Economic Development | Provide information on available office space to all potential users or reference sources | X | X | X | X | X | $6,500 |  | Roswell EDD |
| Economic Development | Work with other City departments to promote public investments such as pedestrian amenities that will result in increasing the tax base | X | X | X | X | X |  |  | Roswell EDD |
| Economic Development | Continue to support quality of life enhancements that make the area attractive to corporations | X | X | X | X | X |  |  | Roswell EDD; planning; other City departments |
| Economic Development | Collaborate with the Convention and Visitors Bureau and others on marketing | X | X | X | X | X | $3,000 |  | Roswell EDD |
| Economic Development | Improve signage to key attractions throughout the City | X | X | X | X | X | $300,000 |  | Roswell EDD; Transp. Dept. |
| Economic Development | Guide small entrepreneurs to available forms of resources and assistance | X | X | X | X | X |  |  | Roswell EDD |
| Economic Development | Communicate with businesses via electronic newsletter to keep them informed of developments in the City | X | X | X | X | X |  |  | Roswell EDD; Community Relations Office |
| Economic Development | Stay involved in regional discussions. | X | X | X | X | X |  |  | Roswell EDD; Fulton County ED; GNFCC |
| Economic Development | Continue to effectively communicate the development process; advocate for streamlining where opportunities exist | X | X | X | X | X |  |  | Community Development |
| Economic Development | Inform applicants of the applicable design/development guidelines | X | X | X | X | X |  |  | Roswell EDD; Planning |
| Redevelopment | Pursue policy-based budgeting to accomplish redevelopment goals, with redevelopment as a priority | X | X | X | X | X |  |  | City Administrator and City Council |
| Redevelopment | Continue to consider locating public facilities in redevelopment target areas | X | X | X | X | X |  |  | City Administrator and City Council |
| Redevelopment | Implement Midtown Roswell Redevelopment Plan (also see specific items below on implementing that plan) | X | X | X | X | X |  |  | City (various departments) |
| Redevelopment | Implement recommendations of revitalization study and plan for the Holcomb Bridge Road corridor east of GA 400 | X | X | X | X | X |  |  | City (various departments) |
| Redevelopment | Reconstitute Downtown Development Authority, if needed. | X | X | X | X | X |  |  | Community Development; City Council |
| Redevelopment | Seek funding for implementation of redevelopment studies, plans, and projects | X | X | X | X | X |  |  | Community Development; City Council |
| Redevelopment | Assist where possible in improving access, ingress and egress to outmoded retail centers and upgrade surrounding road networks | X | X | X | X | X |  |  | Community Development; Transportation |
| Redevelopment | Promote existing retail space and the redevelopment of vacant retail space | X | X | X | X | X |  |  | Roswell EDD |
| Redevelopment | Consider the use of overlay districts to encourage redevelopment opportunities as appropriate | X | X | X | X | X |  |  | MCC |
| Redevelopment (Midtown) | Consider establishing a development response team, responsible for working with property owners on redevelopment projects | X | X | X | X | X |  |  | Community Development |
| Redevelopment (Midtown) | Plan and fund new street networks in conjunction with private redevelopment, where agreement on cost sharing can be attained. | X | X | X | X | X |  | X | Transportation Department; Community Development |
| Redevelopment (Midtown) | Design and install Alpharetta Street streetscape per plan’s recommendations | X | X |  |  |  | $2,955,195.69 |  | Community Development Department; Transportation Department; GDOT |
| Redevelopment (Midtown) | Complete preliminary design of Hog Wallow greenway |  |  | X |  |  |  | X | Recreation and Parks Dept. |
| Historic Preservation | Conduct an intensive-level, comprehensive historic resources survey of the City. Identify all types of historic resources, including buildings and structures, historic landscapes, and historic sites and objects | X | X | X | X | X |  |  | HPC, HCAM, Preservation Planner, SHPO, consultants |
| Historic Preservation | Continue the “legendary chats” program of the Convention and Visitors Bureau (CVB) | X | X | X | X | X |  |  | CVB, UGA |
| Historic Preservation | Develop a citywide GIS database of all identified cultural resources. Update the database periodically as needed | X | X | X | X | X |  |  | GIS; Preservation Planner |
| Historic Preservation | Expand the existing National Register Historic District to include adjacent eligible commercial and residential areas | X | X | X | X | X |  |  | HPC, Preservation Planner, Consultant |
| Historic Preservation | Pursue National Historic Landmarks designations, as appropriate | X | X | X | X | X |  |  | R&P/H&CA |
| Historic Preservation | Develop design guidelines for three character areas (Town Square and Mimosa Boulevard; Mill Village; and Canton Street) of the local Historic District | X | X | X | X | X |  |  | HPC, Preservation Planner, Consultant |
| Historic Preservation | Incorporate mechanisms for protecting heritage trees into the existing Tree Ordinance | X | X | X |  |  |  |  | Community Development |
| Historic Preservation | Continue the series of brochures and town hall meetings currently being used | X | X | X | X | X |  |  | HPC, Preservation Planner |
| Historic Preservation | Enlarge the emphasis of programs and publications from antebellum resources to include resources from all periods of the City’s history. Publish the findings of the Historic Resources Survey and produce a “coffee table” version for sale. Utilize Certified Local Government (CLG) funds for funding survey and book publication | X | X | X | X | X |  |  | HPC, CD, Preservation Planner, SHPO |
| Historic Preservation | Work with the Roswell Convention & Visitors Bureau (CVB) to develop ways to promote the City’s historic sites through the CVB’s already established channels. Meet regularly with all associated local agencies and organizations to discuss promotional programs and to keep all groups updated. Periodically review and update existing programs | X | X | X | X | X |  |  | R&P/H&CA; CVB |
| Historic Preservation | Support development of lesson plans about the City’s historic preservation programs and policies to be used in local heritage education programs. Support the curriculum of the Teaching Museum, which educates Fulton County students about U.S., Georgia, and local history | X | X | X | X | X |  |  | R&P/H&CA; Fulton County Schools |
| Historic Preservation | Make information about the rehabilitation tax credit programs and application forms readily available through as many sources as possible. Provide positive case studies of successful rehabilitation projects | X | X | X | X | X |  |  | HPC, Preservation Planner |
| Historic Preservation | Make information about historic facade easements and conservation easements readily available through as many sources as possible. Provide positive case studies of successful easement donations and their resulting historic resources protection | X | X | X | X | X |  |  | HPC, HCAM, Preservation Planner |
| Historic Preservation | Encourage local banks to establish a low-interest loan pool to provide funding for preservation projects | X | X | X | X | X |  |  | HPC, HCAM, Preservation Planner, local bankers |
| Historic Preservation | Create a repository of information about all aspects of historic preservation and make this resource readily available and accessible to the public. Develop and maintain the collection to also serve as a resource center for the HPC | X | X | X | X | X |  |  | HPC, HCAM, Preservation Planner |
| Historic Preservation | Add a specific historic preservation category to the City’s existing web site to direct people to technical information about historic preservation that is available locally and on the Internet | X | X |  |  |  |  |  | Community Relations Office, Preservation Planner |
| Neighborhoods | Provide limited technical assistance to neighborhood planning efforts in the form of maps, existing zoning and land use, as well as demographic and economic data | X | X | X | X | X |  |  | Community Development |
| Neighborhoods | Encourage neighborhood “self-help” activities | X | X | X | X | X |  |  | Community Development |
| Urban Design | Periodically revise design guidelines, as appropriate | X | X | X | X | X | TBD |  | Community Development; Consultants |
| Urban Design | Implement a gateway master plan for major entrances to the City that incorporates various recommendations of adopted design guidelines | X | X | X | X | X |  |  | Community Development; HPC; DRB; Transportation |
| Urban Design | Install marker to various character areas | X | X | X | X | X | $150,000 |  | Community Development; HPC; DRB; Transportation |
| Urban Design | Continue to apply for federal and state funding to enhance the streetscapes of road corridors in the City | X | X | X | X | X |  |  | Community Development |
| Land Use | Further develop, refine, and implement land use recommendations for “character areas” | X | X | X | X | X |  |  | Community Development |
| Land Use | Periodically report as may be needed on conformance with regional development plan | X | X | X | X | X |  |  | Community Development |
| Land Use | Develop additional policies for specific land uses and incorporate them into the Land Use Element, as specific issues or experiences with them arise | X | X | X | X | X |  |  | Community Development |
| Land Use | Amend the City’s Zoning Ordinance as needed to respond to changing needs and new issues | X | X | X | X | X |  |  | Community Development |
| Land Use | Amend the Future Land Use Plan Map as needed | X | X | X | X | X |  |  | Community Development |
| Community Facilities | Periodically update the City’s parks and recreation master plan as needed | X | X | X | X | X | $30,000 |  | Recreation and Parks |
| Community Facilities | Continue Wetlands Enhancement Demo Project Water Quality Monitoring | X |  |  |  |  | To be completed by volunteer monitors |  | Public Works/ Environmental |
| Community Facilities | Implement the master plan for the Roswell Riverwalk | X | X | X | X | X | $10,000,000 |  | Recreation and Parks |
| Community Facilities | Update and review the technology needs of the City through an Enterprise Resource Planning process for efficiency and increased productivity. | X | X | X |  |  | $5,100,000 |  | Administration |
| Community Facilities | Periodically update the Comprehensive Solid Waste Management Plan, as needed | X | X | X | X | X |  |  | Public Works/ Environmental |
| Community Facilities | Periodically review and modify Sanitation rates and fees to reflect the actual costs of service provision and to further divisions goals |  | X |  |  | X |  |  | Public Works/ Environmental |
| Community Facilities | Prepare, adopt, and periodically revise as appropriate a municipal policy for use of City-owned buildings and grounds by private, non-profit, and other government users | X | X | X | X | X |  |  | Administration |
| Community Facilities | Maintain a system of advisory committees for various City departments and functions to provide for citizen participation and general advice in the overall direction of municipal service provision | X | X | X | X | X |  |  | Various departments |
| Community Facilities | Implement and maintain a customer service policy and action plan in each of the City’s departments, with a consistent level of service throughout the departments | X | X | X | X | X |  |  | Various departments |
| Community Facilities | Monitor the provision of municipal services and their ability to meet the diversifying needs of the City’s population. | X | X | X | X | X |  |  | Administration; Various departments |
| Community Facilities | Implement a community-based approach to policing, including Neighborhood Watch and other appropriate programs of the Crime Prevention Unit | X | X | X | X | X |  |  | Police |
| Community Facilities | Maintain the City’s current Insurance Services Office (ISO) rating of 3 | X | X | X | X | X |  |  | Fire & Rescue |
| Community Facilities | Continue programs of recognition to all firefighters for the jobs they accomplish as a combination department of full time and part time employees. | X | X | X | X | X |  |  | Fire & Rescue; Mayor and City Council |
| Community Facilities | Continue to program and implement improvements needed to maintain and upgrade the Roswell Water Utility, in accordance with the Management Plan | X | X | X | X | X | $1,500,000 |  | Public Works/ Environmental |
| Community Facilities | Periodically review and modify water rates and fees to reflect the actual costs of service provision and to further system goals |  | X |  | X | X |  |  | Public Works/ Environmental |
| Community Facilities | Continue to prioritize road resurfacing projects, drainage maintenance projects, and sidewalk repair projects according to most urgent need | X | X | X | X | X |  |  | Transportation |
| Community Facilities | Investigate the need for traffic calming and integrate traffic calming projects as may be appropriate in the City’s capital plan | X | X | X | X | X |  |  | Transportation |
| Community Facilities | Develop a program incorporating landscaping/ streetscaping into all major road projects to provide greater community identity and safety | X | X | X | X | X |  |  | Transportation; Community Development |
| Community Facilities | Continue to program and implement improvements needed to maintain and upgrade the stormwater management system in compliance with the MS4 NPDES Permit. | X | X | X | X | X | $5,500,000 |  | Public Works/ Environmental; Transportation |
| Community Facilities | Continue to implement TMDL Impaired Stream monitoring efforts and implementation of the WIP’s. | X | X | X | X | X | $275,000 |  | Public Works/ Environmental |
| Community Facilities | Partner with the Atlanta-Fulton County Library System to expand library space in Roswell | X | X | X | X | X |  |  | Administration |
| Community Facilities | Continue to monitor the conditions of municipally owned and operated historic and cultural facilities; schedule improvements to such facilities and grounds as appropriate | X | X | X | X | X |  |  | Historic and Cultural Affairs Manager |
| Community Facilities | Consider plans for additional historic streetscape improvements within the local Historic District | X | X | X | X | X | $2,000,000 | X | Community Development |
| Community Facilities | Maintain and expand, as appropriate, the citizen deputies program of community-based code enforcement | X | X | X | X | X |  |  | Community Development |
| Community Facilities | Prepare, implement, and revise as appropriate a community information plan and programs | X | X | X | X | X |  |  | Community Relations Officer |
| Community Facilities | Continually review and revise the disaster preparedness and emergency management plans in conjunction with Fulton County | X | X | X | X | X |  |  | Various Departments |
| Development Impact Fees | Periodically review and update the development impact fee program, including fees | X |  | X |  | X |  |  | Community Development |
| Transportation | Implement transportation system improvements as described in the Comprehensive Plan and Transportation Master Plan | X | X | X | X | X |  |  | Transportation |
| Intergovt’l Coordination | Periodically revisit and update intergovernmental service agreements |  | X | X |  |  |  |  | Administration |
| Intergovt’l Coordination | Monitor new forms of governance proposed in North Fulton County for their impact on Roswell | X | X | X | X | X |  |  | Administration |
| Intergovt’l Coordination | Periodically revisit and revise the intergovernmental land use dispute resolution process |  | X | X |  |  |  |  | Administration |
| Intergovt’l Coordination | Assist in implementing the Water Supply and Water Conservation Management Plan prepared by the Metropolitan North Georgia Water Planning District | X | X | X | X | X | $15,000/yr |  | Public Works/ Environmental; Community Development |
| Intergovt’l Coordination | Assist in implementing the District-Wide Watershed Management Plan prepared by the Metropolitan North Georgia Water Planning District | X | X | X | X | X |  |  | Public Works/ Environmental |
| Intergovt’l Coordination | Complete watershed improvement planning in connection with the Metropolitan North Georgia Water Planning District’s mandates | X | X | X | X | X | $1,500,000 |  | Public Works/ Environmental |
| Intergovt’l Coordination | Assist in implementing the Big Creek Watershed Study Master Plan | X | X | X | X | X | $50,000 |  | Public Works/ Environmental |